## Gantt_44w
ID | WBS | Phase | Task | Owner | Start (Week) | Duration (Weeks) | End (Week) | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44
P1 | Phase 1 | Inception/Planning | Phase 1: Initiation & Planning (WBS 1.0 + initial 2.0) | PM + Core Team | 1 | 4 | 4 | bar: W1 to W4
1.1 | 1.1 | Inception/Planning | Kickoff & finalize Project Charter | PM (Alex) + Sponsor | 1 | 1 | 1 | bar: W1
1.2 | 1.2 | Inception/Planning | Sponsor authorization & initial budget | CEO/CFO | 1 | 1 | 1 | bar: W1
1.3 | 1.3 | Inception/Planning | Stakeholder register + engagement assessment | PM | 1 | 2 | 2 | bar: W1 to W2
1.4 | 1.4 | Inception/Planning | Define scope validation approach (Exploratory Team) | PM + Steering | 2 | 2 | 3 | bar: W2 to W3
1.5 | 1.5 | Inception/Planning | Scope Mgmt Plan + WBS baseline sign-off | PM + Sponsor | 3 | 2 | 4 | bar: W3 to W4
2.0 | 2.0 | Inception/Planning | Infrastructure & Security readiness (initial) | Ops/Sec | 2 | 3 | 4 | bar: W2 to W4
2.1 | 2.1 | Inception/Planning | AWS cloud environment setup | Network Admin + DevOps | 2 | 2 | 3 | bar: W2 to W3
2.2 | 2.2 | Inception/Planning | Neo4j instance provisioning | Architect + Data Eng | 3 | 2 | 4 | bar: W3 to W4
2.3 | 2.3 | Inception/Planning | Legal & IP compliance audit (kickoff) | Legal Counsel | 3 | 2 | 4 | bar: W3 to W4
P2 | Phase 2 | Core Development | Phase 2: Core Development (WBS 2.0, 3.0, 4.0 - 2-week sprints) | Engineering Team | 5 | 32 | 36 | bar: W5 to W36
3.0 | 3.0 | Core Development | Core AI Development | AI + Backend | 5 | 18 | 22 | bar: W5 to W22
3.1 | 3.1 | Core Development | Define DE-ML syntax (spec + examples) | AI Lead + Architect | 5 | 4 | 8 | bar: W5 to W8
3.2 | 3.2 | Core Development | Develop RAG ingestion pipeline MVP | AI Lead + Data Eng | 7 | 10 | 16 | bar: W7 to W16
3.3 | 3.3 | Core Development | Knowledge graph schema mapping + ingestion tooling | Architect + Data Eng | 9 | 10 | 18 | bar: W9 to W18
3.4 | 3.4 | Core Development | AI agent query + grounding logic (KG + RAG) | AI Lead | 13 | 10 | 22 | bar: W13 to W22
4.0 | 4.0 | Core Development | Interface & Client Integration | Frontend + Backend | 9 | 24 | 32 | bar: W9 to W32
4.1 | 4.1.1 | Core Development | VS Code plugin: Authentication module (LDAP/SSO) | Lead Dev | 9 | 4 | 12 | bar: W9 to W12
4.2 | 4.1.2 | Core Development | VS Code plugin: Context actions ("Explain Code") | Lead Dev | 13 | 4 | 16 | bar: W13 to W16
4.3 | 4.1.3 | Core Development | VS Code plugin: Inline comments renderer (ghost text) | Lead Dev | 17 | 4 | 20 | bar: W17 to W20
4.4 | 4.2.1 | Core Development | Architecture visualization: Graph rendering engine | Frontend Dev | 21 | 6 | 26 | bar: W21 to W26
4.5 | 4.2.2 | Core Development | Architecture visualization: Interactive navigation | Frontend Dev | 27 | 6 | 32 | bar: W27 to W32
4.6 | 4.6 | Core Development | Documentation + developer enablement (rolling) | PM + Leads | 15 | 22 | 36 | bar: W15 to W36
2.4 | 2.4 | Core Development | Security protocols definition + ongoing reviews | Security Lead | 9 | 28 | 36 | bar: W9 to W36
4.7 | 4.7 | Core Development | Sprint ceremonies: reviews + backlog grooming (rolling) | Scrum/PM | 5 | 32 | 36 | bar: W5 to W36
P3 | Phase 3 | Integration/Deployment | Phase 3: Integration & Deployment (WBS 5.0) | Engineering + Ops | 37 | 8 | 44 | bar: W37 to W44
5.1 | 5.1 | Integration/Deployment | Integration kickoff & deployment plan | PM + Leads | 37 | 1 | 37 | bar: W37
5.2 | 5.2 | Integration/Deployment | Staging environment + CI/CD release pipeline | DevOps | 37 | 2 | 38 | bar: W37 to W38
5.3 | 5.1 | Integration/Deployment | RAG pipeline integration (Retriever-Generator link) | AI + Backend | 39 | 2 | 40 | bar: W39 to W40
5.4 | 5.2 | Integration/Deployment | DE-ML parser - database hook integration | Backend | 39 | 2 | 40 | bar: W39 to W40
5.5 | 5.3 | Integration/Deployment | Security integration: PII redaction layer + audit logs | Security + Backend | 40 | 2 | 41 | bar: W40 to W41
5.6 | 5.6 | Integration/Deployment | VS Code extension release candidate packaging | Lead Dev | 41 | 2 | 42 | bar: W41 to W42
5.7 | 5.7 | Integration/Deployment | End-to-end integration testing (cycle 1) | QA + Team | 42 | 1 | 42 | bar: W42
5.8 | 5.8 | Integration/Deployment | Performance tuning + reliability fixes | Engineering | 43 | 1 | 43 | bar: W43
5.9 | 5.9 | Integration/Deployment | Security/legal sign-off | Security + Legal | 43 | 1 | 43 | bar: W43
5.10 | 5.10 | Integration/Deployment | Internal beta release + feedback capture | PM + Team | 43 | 1 | 43 | bar: W43
5.11 | 5.11 | Integration/Deployment | Defect fixes + hardening + schedule buffer | Engineering | 44 | 1 | 44 | bar: W44
5.12 | 5.12 | Integration/Deployment | Go/No-Go decision + incremental rollout kickoff | Sponsor + PM | 44 | 1 | 44 | bar: W44
P4 | Phase 4 | Closure/Handoff | Phase 4: Closure & Handoff kickoff (maintenance continues 3-5 years) | PM + Ops | 44 | 1 | 44 | bar: W44

## Legend
Legend
Summary rows
Milestones
Task bars
Assumption
Weeks are relative (Week 1..44). You can replace Week 1 with an actual start date and re-baseline if needed.
Source (project timeline)
Portfolio-Milestone-Module-4: total duration 44 weeks; Phase 1 = 4 weeks, Phase 2 = 32 weeks, Phase 3 = 8 weeks.